## Project Timeline
Marist Syllabus Evaluator Program
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2020-08-26 | Project Start | -5 | 1
2020-09-02 | Team Meetings set; Client Questions | 5 | 1
2020-09-09 | Project Plan set; Initial UI design | 10 | 1
2020-09-16 | Database draft; Code design draft | 15 | 1
2020-09-23 | 2nd contact with client - review designs | 20 | 1
2020-09-30 | UML diags final; proj plan final | 5 | 1
2020-10-07 | Database finalized | 10 | 1
2020-10-14 | Mid-semester peer reviews due | 15 | 1
2020-10-21 | IT system should be working | 5 | 1
2020-10-28 | Port code from VMs to IT env | 10 | 1
2020-11-04 | First Demo to client | -5 | 1
2020-11-11 | User Validation & Test plan finalized | 10 | 1
2020-11-18 | Deployment at client | -5 | 1
2020-11-25 | Documentation | 5 | 1
2020-11-25 | FINAL PRESENTATION! | 10 | 1
2020-12-09 | contingency | -5 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2020-08-26 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2020-08-26 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2020-08-26 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2020-09-02 | Team Meeting; 1st homework due | Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | All
2020-09-03 | Have more specific req | have more specific requirements via questions and update this do
2020-09-03 | Have DB Req | have plan for DB and other IT/IS req
2020-09-09 | get info about Marist log-in | ask marist IT about the steps necessary to add marist authentication
2020-09-09 |  | Complete mock-ups (ie. wireframes) of your user interface.
2020-09-09 | Homework #2 Due | Initial Design should be drafted… what do you envision the system looking like? Requirements full documented and ready for confirmation with the client. E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams. | All
2020-09-16 | Workable front end | Have a workable front end form (will change a lot but is a start point) HW3 Due: Rough draft of design / UML / use case diagrams / user stories
2020-09-16 | reading in and storing sylbses | read in the file from the web form and also have a method to store,also includes file conversion
2020-09-23 | first round of reading syl | make a prelimainary system to read a syl, figure out if its the right direction to go in
2020-09-23 | figure all IT out | get all IT tasks done
2020-09-23 | Homework #4 Due | Status review: status report & finalized design & draft
2020-09-23 | Item checklist on front end | Complete initial (ie. first pass feedback) peer reviews
2020-09-30 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams
2020-09-30 | Homework #5 Due | HW5: status report & final E/R diagram
2020-10-07 | Database finalized | database finalized
2020-10-14 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews
2020-10-14 | Workable front end | Has front end working
2020-10-21
2020-10-28 | Port code from VMs to IT env. | (Should be able to demo or install something at client by now)
2020-11-04 | First Demo of Prototype | Complete project prototype first-pass demo ready
2020-11-11 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented
2020-11-18 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented
2020-11-18 | Draft Documentation | All documentation required for the project in Draft form
2020-11-25 | Paper Due - Final Documentation | All documentation required for the project in FINAL form
2020-11-25 | FINAL PRESENTATION! | Client will be on hand to accept / reject final project deliverables | All
2020-12-02 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All

## Weeks - Wednesday Section
Week | Class Topics and Activities | Assignments Due | Class Format
8/26 | Introduction; Project case study; Project plan; |  | Online, live webex, and
| Sections and Teams; Project overview |  | in classrooms 2nd floor
9/2 | Client Interview | Homework 1 due: requirements gathering questions & project plans/trello boards | Individual sections
(HC2023 available)
9/9 | IS = Project Mgt primer & team leadership | Homework 2 due: document | Group (HC2023 &
| CS = good design, code repository best practices | showing all requirements | other rooms for
|  | prioritized | breakouts: CS/IT/IS)
9/16 | Project Management and Design tooling | HW 3: rough draft of design / UML / use | Group (HC2023)
| (graphical tools to do mockups or models) | case diagrams / user stories | Algozzine on
project mgt
9/23 | Guest presentation: Alan Labouseur on | HW4: status report & finalized design & draft | Group (HC2023)
| database design and pitfalls | E/R Diagram (if appropriate) | Alan's talk
| Algozzine with IT & IS - review status / equipment |  | basement
9/30 | Status by team in class + work in class | HW5: status report & final E/R diagram | Individual Sections
10/7 | Status / work in class / help | Status report | Individual Sections
10/14 | Status / work in class / help | Status report | Individual Sections
10/21 | Status / work in class / help | Status report | Individual Sections
10/28 | CHECKPOINT: should be able to demo or | Status report | Individual Sections
even install something at client by now
11/4 | Presentation Practice & hints / tips | Status report | Individual Sections
11/11 | Client visit for final install | Status report | Individual Sections
11/18 | Final Presentations to client | Status report | Individual Sections
11/25 | Thanksgiving - NO CLASS
12/2 & 12/9 | Contigency / Hand in all code, documentation, deliverables | Final presentation & Client
documentation are due
Peer evaluations also due
All final docs due (last chance)

## Weekly Status Reports
Status Report - Team name, members
Date | 2020-08-26
RGY | Item | Description | Mitigation / Help needed
Red
Yellow
Green | Form Team | make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later).
Green | Communication Plan | meet and establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch)
Green | Requirement questions | Form a list of questions to ask client regarding requirements of the project.
Green | Project Plan | Further develop the project plan | Need more specific requirements